Project overview - project = "MA" ORDER BY created DESC

Cost overview - project = "MA" AND "Estimated Cost" IS NOT EMPTY ORDER BY "Estimated Cost" DESC –

Fields : estimate cost,actual cost

Step – open excel sheet and add this formula and calculate

| Metric | Formula | Description |
| --- | --- | --- |
| EV | %Done × EstimatedCost | Earned value |
| CV | EV - ActualCost | Cost variance |
| CPI | EV / ActualCost | Cost performance index |
| SV | EV - PlannedValue | Schedule variance |

Upcoming task - project = "MA" AND duedate >= now() AND duedate <= endOfDay(+7d) ORDER BY duedate ASC

Fields:

Resource Reports - project = "MA" AND assignee IS NOT EMPTY ORDER BY assignee

Over-allocated Resource –

Mobile-App – Task Cost Overview = project = "MA" AND issuetype in (Task, Sub-task) AND "Estimated Cost" IS NOT EMPTY ORDER BY duedate

Mobile-App – Progress Report = project = "MA" ORDER BY "Progress (%)" DESC

Add Gadgets

In your Dashboard:

- Filter Results (Detailed View)

  - Columns: Key, Summary, % Done, Start Date, Due Date, Assignee, Status

- Pie Chart Gadget

  - Filter: Mobile-App – Progress Report

  - Statistic: Status

- Created vs Resolved Chart

  - Filter: Mobile-App – Progress Report

  - Period: Weekly

Mobile-App – Critical Tasks = project = "MA" AND "On Critical Path" = Yes

Mobile-App – Milestone Report = project = "MA" AND issuetype = Milestone ORDER BY duedate ASC

🩵 STEP 1: Identify Milestones

In WBS Gantt-Chart, mark milestone tasks:

- Right-click on a task → “Convert to Milestone”

- Milestone tasks appear as diamonds (♦) on your Gantt chart.